## Sheet1
Sprint1
Meetings | Date | Minutes | Meeting Attendees | Decision Items | Discussion Items | Next Meeting Agenda
1 | 2024-02-02 | 1h (3pm-4pm) | Mohamad, Minhtu, Hawraa, Carmen, Amira | Decided Frameworks; We want to give our web app a bit of a unique twist by using a cookie token system | Discussed Project Approach; explored different third-party services that we can integrate | Next meeting all team members must be familiar with the task required for sprint 1; be ready to pitch any other ideas for structuring; think about what they are best at so we can divide the work in a smart way
2 | 2024-02-07 | 4h (10 am to 2pm) | Mohamad, Carmen, Amira, Minhtu, Hawraa | We devided who does what when it comes to the project approach and the other parts of sprint 1; decided on third-party services that we would like to use | We continued discussions on how we want our project to look like; talked about each memebers strengths and weaknesses in order to have the most efficient teamwork | mainly each member must finish their part of sprint 1 so we can do a team review
3 | 2024-02-10 | 1h 30 mins (2h45 pm to 4h15 pm) | Mohamad, Amira, Carmen, Hawraa, Minhtu | In this meeting we checked what was done and missing from sprint 1 | As mentioned, we mainly discussed and reviewed sprint 1; discussed our preparation for sprint 2 | Ideally start coding a bit of each part so we can start discussing more integration of each issue