## Sheet1
Logs | Name | Role | Activities | Time spent (h) | Total hours
1 | MinhTu Chau | Backend Developer | 2024/03/26 to 2024/03/31: Front end: History page. | 3 | 17
|  |  | 2024/03/26 to 2024/04/01: Worked on PDF sent to user after reservation is made. Worked on autofil of user's information from login info when filling a reservation. | 4
|  |  | 2024/04/01 to 2024/04/09: Worked on new feature: Cookie points system. | 7
|  |  | 2024/04/01 to 2024/04/09: Presentation slides. | 3
2 | Mohamad Edelby | Frontend Developer | 2024/03/26 to 2024/04/01 :Front end: History and Payment pages. | 7 | 16
|  |  | 2024/04/01 to 2024/04/07: Debugging unit tests. | 7
|  |  | 2024/04/09: Worked on documentation: meeting minutes. | 2
3 | Carmen Derderian | Backend Developer | 2024/03/26 to 2024/04/01: Worked on PDF sent to user after reservation is made. | 3 | 11
|  |  | 2024/03/26 to 2024/04/05 : Worked on history page back end to handle rservation approval and checkout process. | 5
|  |  | 2024/04/05 to 2024/04/09: Worked on new feature: Cookie points system. | 3
4 | Hawraa Al-Adilee | Backend Developer | 2024/03/26 to 2024/04/01 : Error Handling | 6 | 16
|  |  | 2024/04/10: Worked on documentation: team logs. | 3
|  |  | 2024/03/26 to 2024/03/31: Worked on history page back end to handle rservation approval and checkout process. | 3
|  |  | 2024/04/08 to 2024/04/10: Implementing static analysis tools. | 4
5 | Amira Toslim | Frontend Developer | 2024/03/31 to 2024/04/9: Worked on acceptance tests and Unit tests | 8 | 15
|  |  | 2024/04/01 to 2024/04/07: Debugging unit tests. | 7