## Sheet1
Logs | name | role | activities | Time spent (h) | Total hours
1 | MinhTu Chau | Backend Developer | 2024/02/20 to 2024/03/10: Developped the logic of the reservation of the cars to konow if a car is available or not according to the period of rental of a user. | 10 | 56
|  |  | 2024/02/23 to 2024/02/29: Connected a map API to show the location a cars. | 12
|  |  | 2024/02/20 to 2024/03/10: Worked on connecting the backend with the frontend using Django. | 12
|  |  | 2024/02/20 to 2024/03/10: Worked on the backend for the status of the cars. | 16
|  |  | 2024/02/18-20-25-29: Worked on the frontend | 6
2 | Mohamad Edelby | Frontend Developer | 2024/02/15 to 2024/02/21 : Worked on the home page. | 10 | 40
|  |  | 2024/02/21to 2024/02/24 : Worked on the car listing page | 10
|  |  | 2024/02/24 to 2024/02/27 : Worked on the contact page | 10
|  |  | 2024/02/29to 2024/03/7: worked on the sign in page | 10
3 | Carmen Derderian | Backend Developer | 2024/02/15 to 2024/03/1 : Worked on the login page. | 8 | 63
|  |  | 2024/02/14 to 2024/02/20: Worked on the home page. | 9
|  |  | 2024/02/25 to 2024/02/29 : Worked on the database of the web application. | 15
|  |  | 2024/02/20 to 2024/03/01 : Worked on connecting the backend with the frontend using Django. | 15
|  |  | 2024/03/01 to 2024/03/11 : Worked on the history page of a user. | 16
4 | Hawraa Al-Adilee | Backend Developer | 2024/02/15 to 2024/02/22 : Worked on the frontend of the reservation. | 8 | 60
|  |  | 2024/02/14 to 2024/02/20 : Worked on the home page. | 9
|  |  | 2024/02/23 to 2024/02/29 : Worked on the database. | 15
|  |  | 2024/02/20 to 2024/03/10 : Worked on connecting the backend with the frontend using Django. | 15
|  |  | 2024/02/20 to 2024/03/10 : Worked on the backend of the reservations. | 13
5 | Amira Toslim | Frontend Developer | 2024/02/15 to 2024/02/21 : Worked on the home page. | 10 | 40
|  |  | 2024/02/21to 2024/02/24 : Worked on the car listing page | 10
|  |  | 2024/02/24 to 2024/02/27 : Worked on the contact page | 10
|  |  | 2024/02/29to 2024/03/7: worked on the sign in page | 10