## Sheet1
Sprint2
Meetings | Date | Minutes | Meeting Attendees | Decision Items | Discussion Items | Next Meeting Agenda
1 | 2024-03-27 | 1 hour (10:30 - 11:30) | Mohamad, Minthu, Amira, Hawraa, Carmen | Sprint 4 plan. | We discussed what we ned to complete for sprint 4: a new feature to set us apart. We also looked over what we need to do in order to finalize our web application | For the next meeting, team members must have started their research on possible ideas for new features.
2 | 2024-03-29 | 1 hour 30 minutes (15:30 - 17:00) | Amira, Carmen, Mohamad, Hawraa, Minthu | Sprint 3 fixing. | After our demo with the TA, we observed some missing attributes so we pinpointed what needed to be done to complete sprint 3. | Fix/Complete sprint 3
3 | 2024-03-30 | 4 hours | Mohamad, Carmen, Hawaraa, Minthu, Amira | Sprint 3 validation, Decision on feature | This meeting was to validate that what we had to fix from sprint 3 was indeed completed. After that, we decided what our feature was gonna be: a cookie point system that will permt users to get discounts based on a loyalty point system | Start implementing the feature
4 | 2024-03-31 | 2 hours | Carmen, Hawraa, Minhtu | Backend for the cookie points system | The three team members discussed how to implement the cookie point system: How to save the points to the accounts, how to apply them when needed, how it would work. | Apply point system to backend
5 | 2024-04-02 | 1h30 | Mohamad, Amira | Acceptance test and Test cases. | Discussing the appropriate test cases to code. Both teammates agreed on it and divided the tasks equally. | Fix slight code problems in some of the unit testing.
6 | 2024-03-05 | 2h30 | Hawraa, Carmen, Amira, Mohamad, Minthu | Sprint 4 progress validation. | In this meeting, we presented what we had so far for sprint 4 and validated it with the other teammates and see what else needed to be done. There was still issues with the unit testing, | Complete documentation, fixing bugs related to users and reservations with the cookie point system
7 | 2024-04-07 | 4h15 | Minthu, Carmen, Hawraa | Backend issues | Fix all the issues with the backend: there was a bug regarding the reservations and accounts. There was also issues with pull and merge for some teammates. | Finalize all required backend coding.
8 | 2024-04-09 | 2 hours | Mohamad, Amira | Documentation and unit testing. | Discussing the remaining of sprint 4 documentation to be completed such as sequence and actvity diagrams, meeting minutes, and logs. They also worked on unit testing. | Complete documentation.
9 | 2024-04-10 | 1 hour | Mohamad, Hawraa, Minthu, Amira, Carmen | Finalizing Sprint 4 | In this meeting, we made sure that everything for sprint4 was done, the documentation, the unit testing, the new feature was working properly.