## Sheet1
Sprint2
Meetings | Date | Minutes | Meeting Attendees | Decision Items | Discussion Items | Next Meeting Agenda
1 | 2024-03-13 | 1 hour (10:30 - 11:30) | Mohamad, Minthu, Amira, Hawraa, Carmen | Sprint 3 plan. | We discussed the different parts of the project that we have to acomplish for Sprint 3. This includes: Find a branch, check-in, and checkout. We also assigned team members to the unit testing of sprint 3. | For the next meeting, team members must have started their research on how to incorporate their designated part.
2 | 2024-03-15 | 1 hour 30 minutes (15:30 - 17:00) | Amira, Carmen, Mohamad, Hawraa, Minthu | Sprint 2 demo, and fixing. | We first had our demo to the ta for Sprint 2. After the demo, we discussed what we need to fix depending the feedback we got from the ta. | Fix/Complete sprint 2: manage reservations, add confirmation message when reserving, be able to add cars from front end, and test cases
3 | 2024-03-16 | 4 hours (11:00 - 15:00) | Mohamad, Carmen, Hawaraa, Minthu, Amira | Sprint 2 validation, backend installation problems, and sprint 3 continuous. | This meeting was to validate that what we had to fix from sprint 2 was indeed completed. After that, we had to help 2 team members installing the backend on their devices as they were having problems. Finally, we continued discussing sprint 3. | Work on adding cars from the frontend.
4 | 2024-03-18 | 2 hours (16:00 - 18:00) | Carmen, Hawraa | Check-in and Checkout Process. | The two team members discussed how to implement check-in and checkout processes. Realated to those are the rantal agreements, and the banking system (deposit and general banking). | Fix email and admin issues.
5 | 2024-03-20 | 1 hour | Mohamad, Amira | Acceptance test and Test cases. | Both team members are responsible of acceptance and unit testing, so during this time they discussed each of their parts, and that there were no issues with integrating these tests to the backend. | Fix slight code problems in some of the unit testing.
6 | 2024-03-22 | 2 hours 15 minutes (14:45 - 17:00) | Hawraa, Carmen, Amira, Mohamad, Minthu | Sprint 3 progress validation. | In this meeting, we presented our porgress so far of sprint 3 to the ta and got feedback from it. We demonstarted that we added the feature of adding cars from the frontend. Working database. | Complete documentation, fixing check-in and checkout, and making history of reservations.
7 | 2024-03-23 | 3 hours 45 minutes (12:15 - 16:00) | Minthu, Carmen, Hawraa | Backend issues and banking. | There were mutliple things regarding backend that needed to be fixed. First, the cars weren't appearing because of bugs with backend but was fixed during the meeting. Second, no one was able to pull or merge anything but was fixed by using .gitignore. Finally, they discussed how we were going to integrate a banking system for rental payments and deposits. | Finalize all required frontend and backend coding.
8 | 2024-03-24 | 2 hours | Mohamad, Amira | Documentation and unit testing. | Discussing the remaining of sprint 3 documentation to be completed such as sequence and actvity diagrams, wiki, meeting minutes, and logs. They also validated that all unit testing was working accordingly without any errors. | Complete documentation.
9 | 2024-03-25 | 1 hour (21:00 - 22:00) | Mohamad, Hawraa, Minthu, Amira, Carmen | Finalizing Sprint 3 | In this meeting, we made sure that everything for Sprint 3 was done such as the layout of the web app with frontend. Also, verified that all backend is working like: reservations, history, adding cars, and car returns. Finally verified unit tests functionality and wrapped up documentation. | Plan for Sprint 4